# Scope of Work: Canva B2B Data Pipeline Enhancement

## Service Delivery Engagement

## Executive Summary

Snowflake Service Delivery will partner with Canva to design, implement, and operationalize a scalable ingestion pattern for ingesting B2B lead data from third-party sources (Splash, Goldcast, RainFocus, G2) into their Snowflake-based data pipeline using OpenFlow. This engagement includes establishing monitoring and alerting frameworks, implementing the first integration, and enabling Canva’s operations team to independently launch subsequent integrations.

Key Deliverables: - Ingestion pattern design and documentation - Monitoring and alerting framework on OpenFlow - First third-party source integration (reference implementation) - Knowledge transfer and operational runbooks - Hypercare support for production stabilization

Timeline: 20 weeks (16 weeks core implementation + 4 weeks hypercare) Total Estimated Effort: 903 hours

## 1. Project Scope

### 1.1 In Scope

#### 1.1.1 Architecture & Design

- Review and document current B2B data pipeline architecture

- Design scalable ingestion pattern for third-party sources

- Evaluate transformation placement options (OpenFlow vs. Snowflake native)

- Create architectural decision records (ADRs) with pros/cons analysis

- Design monitoring and alerting framework for data pipelines

- Define configuration-driven approach for new source onboarding

- Recommend architectural and pattern changes based on any limitations identified in current state components (OpenFlow, DynamoDB, etc.)

#### 1.1.2 Implementation

- Build monitoring and alerting capabilities for data pipelines

- Verify and enhance ingestion receiver infrastructure

- Create transformation templates for field mapping and validation

- Build error handling and dead-letter queue patterns

- Configure simple monitoring dashboards and alerts for operations team

- Integrate first third-party source (Splash, Goldcast, or RainFocus - TBD)

#### 1.1.3 Documentation & Knowledge Transfer

- Architecture documentation (current and future state)

- Pattern implementation guide for ingestion integrations

- Configuration templates and examples

- Operations runbooks for common scenarios

- Troubleshooting guides

- Training sessions for Canva operations team

#### 1.1.4 Handover & Hypercare

- Structured handover to Canva operations team

- 4-week hypercare support post-implementation

- Guided implementation of second source with operations team

- Performance tuning and optimization

- Issue resolution and escalation support

### 1.2 Out of Scope

The following items are explicitly excluded from this engagement:

- AI/ML integration and Snowflake Intelligence implementation

- Clay enrichment data integration

- Optimization of Salesforce/Braze outbound pipelines

- Changes to DynamoDB (PPS/BPS) architecture

- Migration of existing 50-60 internal forms (already completed)

- Implementation of sources beyond the first reference implementation (Canva team will implement 2-4 additional sources)

- Fivetran replacement for non-lead data pipelines

- IPO readiness workstreams unrelated to B2B data pipeline

### 1.3 Assumptions

- Canva provides timely access to required environments and documentation

- Third-party source (for first implementation) provides ingestion endpoint or API access

- OpenFlow production environment is stable and accessible

- Canva operations team is available for training sessions

- API credentials and access to third-party platforms will be provided by Canva

- Current DynamoDB to Snowflake CDC pipeline is stable

- Canva technical team is available for technical reviews through implementation

- Ingestion infrastructure (receiver endpoints, authentication/authorization, rate limiting, request validation, async processing queue) is already set up by Canva or will be provided as a foundation

- Architectural and pattern changes will be made based on any limitations identified in current state architecture components (including OpenFlow, DynamoDB, etc.) during the design and implementation phases

## 2. Project Phases & Deliverables

### Phase 1: Discovery & Architecture Design (Weeks 1-3)

#### Objectives

- Understand current architecture in detail

- Design scalable integration patterns

- Define monitoring framework requirements

- Align on technical approach with Canva team

#### Activities

Week 1: Current State Assessment - Conduct architecture deep-dive sessions with Canva team - Review existing OpenFlow pipelines and configurations - Document current data flow (external sources → OpenFlow → DynamoDB → Snowflake → OpenFlow → Salesforce) - Review B2B Express schema and data models - Assess current monitoring capabilities and gaps - Review third-party source documentation (Splash, Goldcast, RainFocus, G2)

Week 2: Pattern Design - Design ingestion receiver architecture - Define transformation approach and placement - Design error handling - Design idempotency and duplicate detection strategy - Create configuration-driven framework design - Design monitoring and alerting framework - Evaluate and document architectural options with pros/cons - Suggest changes to current state ingestion mechanism and/or technologies based on assessment

Week 3: Design Review & Alignment - Present design options to Canva stakeholders - Conduct technical design review sessions - Finalize architecture decisions (ADRs) - Define success metrics and KPIs - Prioritize first third-party source for implementation - Create detailed implementation plan

#### Deliverables

- ✅ Current State Architecture Documentation

- ✅ Future State Architecture Design

- ✅ Architectural Decision Records (ADRs)

- ✅ Ingestion Pattern Specification

- ✅ Monitoring Framework Design Document

- ✅ Implementation Plan and Timeline

### Phase 2: Monitoring Framework Implementation (Weeks 4-6)

#### Objectives

- Build monitoring and alerting capabilities for the data pipeline

- Create simple operational dashboards

- Enable operations team to monitor pipeline health

- Unblock production release of existing 50-60 forms

#### Activities

Week 4: Monitoring Setup - Configure monitoring components for the data pipeline - Set up logging and metrics collection - Implement pipeline health checks - Create data quality validation checks - Define alerting rules and thresholds

Week 5: Dashboard & Alerting - Build simple operational dashboards using Snowflake Dashboards or Streamlit (pipeline status, throughput, errors) - Configure alert notifications (email, Slack, PagerDuty, etc.) - optional, pending system-related blockers - Implement performance metrics tracking (latency, SLO) - Create simple data quality dashboards (row counts, null rates, schema validation)

Week 6: Testing & Documentation - Test monitoring across existing forms - Validate alert triggers and notifications - Create monitoring operations guide - Train operations team on dashboard usage - Document monitoring configuration for new sources

#### Deliverables

- ✅ Monitoring and Alerting Capabilities

- ✅ Simple Operational Dashboards (Snowflake Dashboards or Streamlit)

- ✅ Alert Configuration (if no system blockers)

- ✅ Monitoring Operations Guide

- ✅ Training Session for Operations Team

### Phase 3: Ingestion Pattern Implementation (Weeks 7-12)

#### Objectives

- Build reusable ingestion pattern

- Create configuration templates

- Implement transformation and validation logic

- Establish error handling patterns

#### Activities

Week 7: Infrastructure Verification - Verify ingestion receiver endpoints setup - Verify authentication/authorization implementation - Verify rate limiting and throttling configuration - Verify request validation setup - Verify async processing queue implementation

Weeks 8-9: Transformation & Processing - Build transformation templates (field mapping, value constraints) - Implement configuration-driven transformation engine - Build error handling - Implement dead-letter queue for failed records - Develop comprehensive unit tests for transformation logic - Create transformation configuration documentation

Weeks 10-11: Integration & End-to-End Testing - Integrate ingestion receiver with OpenFlow - Implement connection to DynamoDB (PPS/BPS) or other pattern changes agreed upon in design phase - Test end-to-end data flow - Validate transformation logic - Test error scenarios - Conduct integration testing across all components - Document test results and findings

Week 12: Optimization & Documentation - Performance testing and tuning - Implement post-testing changes based on outcomes from integration testing - Create configuration templates - Prepare for first source integration

#### Deliverables

- ✅ Ingestion Pattern

- ✅ Transformation Templates and Engine

- ✅ Error Handling Logic

- ✅ Configuration Framework

- ✅ Configuration Template Library

- ✅ Unit and Integration Tests

### Phase 4: First Source Integration (Weeks 13-15)

#### Objectives

- Implement first third-party source as reference

- Validate pattern in production

- Ensure data flows meet SLA requirements

- Demonstrate operational readiness

#### Activities

Week 13: Source Configuration - Review third-party source API/ingestion documentation - Configure source-specific transformations - Set up authentication and credentials - Create source configurations - Configure monitoring for new source

Week 14: Implementation & Testing - Implement source-specific ingestion handler - Configure field mappings and validations - Test data ingestion from third-party source - Validate data quality in DynamoDB and Snowflake - Test error handling and recovery scenarios - Conduct UAT with Canva team

Week 15: Production Deployment - Deploy to production environment - Monitor initial data flow - Validate SLA compliance (15-minute target) - Performance tuning as needed - Prepare deployment runbook and obtain Canva approval

#### Deliverables

- ✅ First Third-Party Source Integration (Production-Ready)

- ✅ Source-Specific Configuration

- ✅ Validation Test Results

- ✅ Production Deployment Documentation

- ✅ Deployment Runbook (approved by Canva)

### Phase 5: Knowledge Transfer & Handover (Week 16)

#### Objectives

- Transfer knowledge to Canva operations team

- Create comprehensive operational documentation

- Prepare team for independent operation

#### Activities

Week 16: Training & Documentation - Conduct architecture and design training session - Conduct hands-on implementation training - Conduct operations and troubleshooting training - Create operational runbooks - Create troubleshooting guides

#### Deliverables

- ✅ Training Sessions (Architecture, Implementation, Operations)

- ✅ Operational Runbooks

- ✅ Troubleshooting Guides

### Phase 6: Hypercare Support (Weeks 17-20)

#### Objectives

- Provide elevated support during stabilization period

- Monitor system performance and stability

- Address issues and optimize as needed

- Enable self-service source onboarding

- Ensure smooth transition to BAU operations

#### Activities

Weeks 17-20: Post-Production Support - Daily monitoring of pipeline health (Week 17) - Regular check-ins with operations team (3x per week → 2x → 1x) - Issue triage and resolution support - Performance optimization as needed - Documentation updates based on operational feedback - Guide operations team through second source configuration - Review and provide feedback on their implementation - Conduct handover readiness assessment - Formalize handover checklist and sign-off - Final knowledge transfer session

Support Model: - Week 17: Daily sync, active monitoring, immediate response - Week 18: 3x per week sync, proactive monitoring - Week 19: 2x per week sync, reactive support - Week 20: 1x per week sync, escalation support only

#### Deliverables

- ✅ Daily/Weekly Status Reports

- ✅ Issue Resolution Log

- ✅ Performance Optimization Report

- ✅ Updated Documentation (based on operational learnings)

- ✅ Second Source Configuration (Guided)

- ✅ Handover Checklist and Sign-off

- ✅ Hypercare Closeout Report

- ✅ Transition to BAU Support

## 3. Project Timeline

### 3.1 High-Level Timeline Overview

20-Week Project Timeline (16 weeks core + 4 weeks hypercare)

Week:  1    2    3    4    5    6    7    8    9   10   11   12   13   14   15   16   17   18   19   20
       │────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────│
       
Phase 1: Discovery & Design
       [════════════════════]
       │    Design    │    │
       └─────────────────────> Design Approval (Week 3)

Phase 2: Monitoring Framework
                           [════════════════════]
                           │   Monitoring   │
                           └──────────────────────> Monitoring Live (Week 6)

Phase 3: Ingestion Pattern Implementation
                                              [══════════════════════════════════════════════════]
                                              │           Ingestion Pattern           │
                                              └──────────────────────────────────────────────────> Pattern Complete (Week 12)

Phase 4: First Source Integration
                                                                                                  [════════════════════]
                                                                                                  │  First Source  │
                                                                                                  └────────────────────> Production Live (Week 15)

Phase 5: Knowledge Transfer
                                                                                                                        [══════]
                                                                                                                        │  KT  │
                                                                                                                        └─────> Training Complete (Week 16)

Phase 6: Hypercare & Handover
                                                                                                                              [════════════════════════════════]
                                                                                                                              │        Hypercare        │
                                                                                                                              └────────────────────────────────> BAU Transition (Week 20)

Key Milestones:
  ◆ Week 1:  Project Kickoff
  ◆ Week 3:  Design Approval (Go/No-Go)
  ◆ Week 6:  Monitoring Live (Unblock forms)
  ◆ Week 12: Pattern Complete
  ◆ Week 15: First Source Live in Production
  ◆ Week 16: Training Complete
  ◆ Week 20: Handover Complete & BAU Transition

### 3.2 Detailed Schedule

| Phase | Duration | Start Week | End Week | Key Milestone |
| --- | --- | --- | --- | --- |
| Phase 1: Discovery & Design | 3 weeks | Week 1 | Week 3 | Design Approval |
| Phase 2: Monitoring Framework | 3 weeks | Week 4 | Week 6 | Monitoring Live |
| Phase 3: Ingestion Pattern | 6 weeks | Week 7 | Week 12 | Pattern Complete |
| Phase 4: First Source | 3 weeks | Week 13 | Week 15 | Production Live |
| Phase 5: Knowledge Transfer | 1 week | Week 16 | Week 16 | Training Complete |
| Phase 6: Hypercare & Handover | 4 weeks | Week 17 | Week 20 | BAU Transition |

### 3.3 Critical Milestones

| Milestone | Target Week | Importance |
| --- | --- | --- |
| Project Kickoff | Week 1 | Project start |
| Design Approval | Week 3 | Go/No-Go decision point |
| Monitoring Live | Week 6 | Unblock forms release |
| Pattern Complete | Week 12 | Core deliverable |
| First Source Live | Week 15 | Production deployment |
| Training Complete | Week 16 | Team enablement |
| Handover Complete | Week 20 | BAU transition |

## 4. Resource Plan

### 4.1 Snowflake Service Delivery Team

| Role | Responsibility |
| --- | --- |
| Lead Consultant / Architect | Overall project leadership, architecture design, stakeholder management, technical reviews |
| Solution Architect | Implementation lead, transformation logic, integration development, testing |
| OpenFlow Specialist | Monitoring framework, pipeline design, OpenFlow best practices, troubleshooting |
| Engagement Manager | Project management, coordination, status reporting, stakeholder communication |

### 4.2 Canva Team Requirements

| Role | Time Commitment | Phases |
| --- | --- | --- |
| Jeno (Technical Lead) | 4-6 hours/week | Weeks 1-15 (before leave) |
| Data Engineer/Architect | 4-6 hours/week | All phases |
| Dave | 2-4 hours/week | Phases 2-6 |
| Narmina & Ops Team | 8-10 hours/week | Phases 5-6 (training & handover) |
| Adrian | 2-3 hours/week | As needed |

## 5. Cost Estimate

### 5.1 Effort Summary by Phase

| Phase | Hours |
| --- | --- |
| Phase 1: Discovery & Design | 147 |
| Phase 2: Monitoring Framework | 177 |
| Phase 3: Ingestion Pattern | 294 |
| Phase 4: First Source Integration | 135 |
| Phase 5: Knowledge Transfer | 55 |
| Phase 6: Hypercare & Handover | 95 |
| Total Project Hours | 903 |

### 5.2 Effort Summary by Role

| Role | Hours |
| --- | --- |
| Lead Consultant / Architect | 340 |
| Solution Architect | 415 |
| OpenFlow Specialist | 48 |
| Engagement Manager | 100 |
| Total | 903 |

### 5.3 Cost Assumptions & Exclusions

Included in Estimate: - All activities outlined in Phases 1-6 - First third-party source integration - Training and documentation - 4-week hypercare support - Standard project management overhead

Not Included in Estimate: - Implementation of 2nd-5th third-party sources (Canva team will implement using pattern) - Costs for third-party API usage or licenses - Snowflake compute/storage costs - Infrastructure costs for ingestion hosting

## 6. Deliverables Summary

### 6.1 Documentation Deliverables

| Deliverable | Audience |
| --- | --- |
| Current State Architecture Documentation | Technical team |
| Future State Architecture Design | Technical team |
| Architectural Decision Records (ADRs) | Technical team |
| Ingestion Pattern Specification | Developers |
| Monitoring Framework Design Document | Ops & Engineering |
| Configuration Template Library | Ops team |
| Operational Runbooks | Operations team |
| Troubleshooting Guides | Operations team |
| Training Materials | Operations team |

### 6.2 Technical Deliverables

| Deliverable | Description |
| --- | --- |
| Monitoring Framework | Pipeline monitoring, alerts, simple dashboards |
| Ingestion Pattern | Endpoint, auth, validation, processing |
| Transformation Templates | Reusable transformation logic |
| Configuration Framework | Config-driven source onboarding |
| Error Handling Patterns | DLQ, alerting |
| First Source Integration | Production-ready integration (Splash/Goldcast/RainFocus) |
| Test Suite | Unit, integration, end-to-end tests |

### 6.3 Knowledge Transfer Deliverables

| Deliverable | Duration |
| --- | --- |
| Architecture & Design Training | Half day |
| Hands-on Implementation Training | Half day |
| Operations & Troubleshooting Training | Half day |
| Guided Second Source Implementation | During hypercare |
| Office Hours (during hypercare) | As needed |

## 7. Risks & Mitigation Strategies

### 7.1 Schedule Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Jeno unavailable before April | Medium | High | Prioritize critical reviews in Weeks 1-15; document decisions thoroughly |
| Third-party API delays | Medium | Medium | Engage third-party vendors early; have backup source option |
| Scope creep | Medium | Medium | Strict change control; separate “nice-to-have” for Phase 2 |
| Holiday/vacation scheduling | Low | Low | Identify key dates early; plan around holidays |

### 7.2 Technical Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| OpenFlow or current architecture limitations | Medium | High | Architectural patterns will be adjusted based on identified limitations; alternative approaches designed in Phase 1 |
| Performance issues at scale | Medium | High | Early load testing; architecture review by Snowflake experts |
| Integration complexity higher than expected | Medium | Medium | Buffer hours in estimates; early POC in Phase 3 |
| Security/compliance requirements | Low | Medium | Early security review in Phase 1; involve security team |
| Data quality issues | Medium | High | Comprehensive validation; staging environment testing |

### 7.3 Organizational Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Operations team bandwidth constraints | Medium | Medium | Focused training; flexible scheduling; recorded sessions |
| Stakeholder alignment issues | Low | High | Regular status updates; early design reviews |
| Knowledge retention after Jeno’s leave | Medium | High | Comprehensive documentation; cross-train multiple team members |
| Competing priorities | Medium | Medium | Executive sponsorship; clear communication |

## 8. Assumptions & Dependencies

### 8.1 Key Assumptions

- Environment Access: Snowflake team will receive full access to OpenFlow production and development environments by project kickoff

- Data Access: Access to B2B Express schemas, DynamoDB structure, and sample data will be provided

- Third-Party Documentation: API documentation for Splash, Goldcast, RainFocus is available and complete

- Credentials: API keys and authentication credentials for third-party sources will be provided by Canva

- Team Availability: Canva technical team available for weekly design reviews and bi-weekly status meetings

- OpenFlow Stability: OpenFlow platform is production-ready and stable for new implementations

- Infrastructure: Ingestion hosting infrastructure is available or can be provisioned quickly

- Approval Process: Technical decisions can be approved within 3-5 business days

### 8.2 Critical Dependencies

| Dependency | Owner | Required By | Risk Level |
| --- | --- | --- | --- |
| OpenFlow environment access | Canva | Week 1 | High |
| Third-party API documentation | Canva | Week 2 | High |
| Schema and data model documentation | Canva | Week 1 | Medium |
| API credentials for first source | Canva | Week 13 | High |
| Operations team availability for training | Canva | Phase 5 | Medium |
| Design approval from stakeholders | Canva | Week 3 | High |
| Ingestion infrastructure foundation | Canva/IT | Week 7 | Medium |

## Appendix A: Acronyms & Glossary

| Term | Definition |
| --- | --- |
| ADR | Architectural Decision Record |
| API | Application Programming Interface |
| BAU | Business As Usual |
| B2B Express | Canva’s Snowflake database for B2B data (3 schemas: source, model, target) |
| CDC | Change Data Capture (tool for DynamoDB → Snowflake replication) |
| DLQ | Dead Letter Queue (for failed messages) |
| KPI | Key Performance Indicator |
| NiFi | Apache NiFi (basis for OpenFlow) |
| OpenFlow | Snowflake’s data integration tool |
| PPS/BPS | Backend service on DynamoDB for lead processing |
| SLA | Service Level Agreement (15 minutes for Canva) |
| SLO | Service Level Objective (2-5 minutes target for Canva) |
| UAT | User Acceptance Testing |

End of Scope of Work Document